# Food Waste Recycling Service – Project Update

This briefing provides Members with an update on preparations for the launch of Fenland District Council’s new weekly Food Waste Recycling Service, including the service launch date, food waste caddy deliveries, vehicle delivery and communications activity.

Please find included within this Member e-briefing pack a selection of materials and links providing further detail on the rollout:

- Press Release – announcing the service launch date from 7 September 2026 and food waste caddy deliveries from 13 July 2026 (publication date: Tomorrow, 7 July).

- Food waste instruction leaflet – to be delivered to all households inside their food waste caddies, explaining how to use the service. A hard copy of this leaflet will be available in Member cubby-holes on 13 July.

- Food waste social toolkit – for sharing on social media.

- Food waste service FAQs – these will be updated regularly in response to customer feedback. A hard copy of these FAQs will be available in Member cubby-holes on 13 July.

- Final ‘Waste and Recycling in Fenland’ leaflet – this provides an overview of all waste and recycling services in Fenland. It will be delivered inside food waste caddies, alongside the instruction leaflet. A hard copy of this leaflet will be available in Member cubby-holes on 13 July.

## Service launch date and food waste caddy deliveries

We can confirm that the food waste recycling service will go live in Fenland week commencing 7 September 2026.

To help households prepare, deliveries of new food waste caddies will begin week commencing Monday 13 July and continue for around six weeks. More than 90,000 caddies will be delivered to over 45,000 homes across the district during the rollout.

Every household will receive:

- A 5‑litre indoor caddy – for collecting food waste in the kitchen

- A roll of caddy liners – to make the process easier and help keep the caddy clean

- A larger 23‑litre outdoor caddy – to place out for weekly collection

- An instruction leaflet – explaining how to use the new service

This first phase of household caddy deliveries is expected to be complete by the end of August.

Residents can then start using their caddies the week commencing 31 August, a week before collections begin on 7 September.

Caddies will be delivered to all Phase 1 households as follows:

| Area | Delivery completed by |
| --- | --- |
| Whittlesey/Coates/Benwick/Turves/Westry | 20 July |
| Wimblington/Doddington/ Manea/Stonea/Mepal/Forty Foot | 23 July |
| Chatteris/Somersham | 29 July |
| March/Christchurch | 6 August |
| Coldham/Rings End/Thorney Toll/Elm/Friday Bridge | 11 August |
| Begdale/Leverington Common/ Wisbech St Mary/Murrow/Guyhirn | 13 August |
| Leverington/Gorefield/Parson Drove/Newton/Tydd | 17 August |
| Wisbech | 25 August |

Caddy deliveries to town centre flats and communal properties will form Phase 2 of the service rollout later this year and will be tailored to the needs of each property. We’ll update you further on this nearer the time.

## Food waste collection vehicle update

The Council’s eight food waste collection vehicles are now fully built and undergoing final pre-delivery checks. We expect them onsite within a week.

## Communications plan

A comprehensive communications plan, led by Cllr Steve Tierney, is being implemented to ensure residents are fully informed and prepared for the new service.

Completed activity:

- Rebrand of all waste and recycling service materials to ensure a consistent look and feel across all services, including blue and green bins, and garden waste, trade waste and bulky waste services.

- Launch of a dedicated webpage: fenland.gov.uk/foodwaste, including regularly updated FAQs.

- Information packs for Members, town and parish councils, and landlords.

- Food waste service information in the bi-annual bin calendars delivered to all households in November 2025 and March 2026.

- Social media video explainer and press engagement.

- Recruitment day materials, including banners, social media and press engagement.

Upcoming activity:

- Food waste liveries applied to the new food waste vehicles

- Delivery of the food waste instruction leaflet with caddies

- A seven-week social media campaign during the caddy delivery period

- Friendly ‘No food in here please’ materials to encourage correct bin use and participation in the service.

## Key communications messages

- New service to meet national food waste legislation: Funded by Government, so no strain on local taxpayers.

- Same collection day: You’ll receive an indoor food waste caddy and a larger outdoor caddy. The outdoor caddy will be collected on the same day as your blue and green bins.

- Weekly collections: With food waste collected every week, you’ll have more space in your green bin and fewer smells, as food is removed more often.

- Good for the environment: Instead of being sent to landfill or energy from waste plants, your food waste will be recycled into clean, green energy and fertiliser for local farms.

- Optional: We’re confident you’ll enjoy the benefits, but you don’t have to use the service if you don’t want to.

## Recruitment and staffing

The recruitment day held in January 2026 exceeded expectations, with over 100 people attending. Following interviews and assessments, 20 refuse drivers and collectors have been appointed. They will begin their roles in July 2026, supporting the operational setup and assisting with the delivery of caddies and bins ahead of the service launch.

## Funding update

As you’re aware, the new service is funded by the Government’s Department for Environment, Food and Rural Affairs (Defra), which has provided Fenland District Council with:

- £1,061,991 in capital funding, and

- £379,000 of transitional revenue funding

- New Burdens Grant Funding towards revenue costs

## For further information, please contact:

- Cllr Steve Tierney, Portfolio Holder for Recycling and Refuse Collection: STierney@fenland.gov.uk

- Mark Mathews, Head of Environmental Services: mmathews@fenland.gov.uk

- Carol Pilson, Corporate Director: cpilson@fenland.gov.uk